## Gantt Chart Template
GANTT CHART | [27 empty] | https://goo.gl/PXLbMe
| PROJECT TITLE | E4DSE PID Control of temperature in a thermo box |  |  |  |  | COMPANY NAME | [8 empty] | Aarhus School of Engineering Herning - Elektronik
| PROJECT MANAGER | Lasse A. Frederiksen & Kim Nielsen |  |  |  |  | DATE | [8 empty] | Spring 2018
| TEAM | Kim Nielsen, Mads Villadsen, Lasse A. Frederiksen & Jesper Hjort
[6 empty] | Define project |  |  |  |  | Construction |  |  |  |  | Modeling |  |  |  |  | Analysis |  |  |  |  | Control | [9 empty] | Wrap up
| TASK TITLE | TASK OWNER | START DATE | DUE DATE | PCT OF TASK COMPLETE | WEEK 14 |  |  |  |  | WEEK 15 |  |  |  |  | WEEK 16 |  |  |  |  | WEEK 17 |  |  |  |  | WEEK 18 |  |  |  |  | WEEK 19 |  |  |  |  | WEEK 20
[6 empty] | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F
Construction
| Find and construct or order components |  | 2018-09-04 | 2018-11-04 | 100% | bar: WEEK 15 M to WEEK 15 W
| Build the physical system |  | 2018-10-04 | 2018-11-04 | 100% | bar: WEEK 15 T to WEEK 15 W
| Decide system requirements |  | 18/4 | 20/4 | 100% | bar: WEEK 16 W to WEEK 16 T
| Define the physical limits to the system |  | 13/4 | 19/4 | 100% | bar: WEEK 15 F to WEEK 16 T
Modeling
| Make 3 data sets from step response |  | 16/4 | 19/4 | 100% | bar: WEEK 16 M to WEEK 16 T
| Import data sets to matlab |  | 18/4 | 20/4 | 100% | bar: WEEK 16 W to WEEK 16 F
| Estimate transfer function from above data sets |  | 23/4 | 25/4 | 100% | bar: WEEK 17 M to WEEK 17 W
| Adjust requirements based on the system dynamics |  | 27/4 | 27/4 | 100% | bar: WEEK 17 F
Control
| Build and simulate control in Simulink |  | 25/4 | 27/4 | 75% | bar: WEEK 17 W to WEEK 17 F
| Verify the model |  | 30/4 | 2018-03-05 | 25% | bar: WEEK 18 M to WEEK 18 W
Realisation
| Build controller |  | 2018-03-05 | 2018-07-05 | 0% | bar: WEEK 18 T to WEEK 19 M
| Verify controller |  | 2018-08-05 | 2018-11-05 | 0% | bar: WEEK 19 T to WEEK 19 F
| Short report with documentation on the construction |  | 2018-11-05 | 18/5 | 2% | bar: WEEK 20 M to WEEK 20 F
Colours
Kim
Lasse
Jesper
Mads
All